## Sheet1
Bugs | Date found | Date fixed
Bumping into someone while knocked down causes them to get back up immediately | 2018-02-26
Getting hit doesn't interrupt charging | 2018-02-12 | 2018-02-14
Players can charge their meter while in the vine trap | 2018-02-09 | 2018-02-16
Using the Analog stick to crouch lets you move while crouching, while the D-pad doesn't. | 2018-02-09 | 2018-02-14
Players can block after getting hit by the first hit of the Death super | 2018-02-09 | 2018-02-14
The invincible uppercut can be interrupted, and players keep invincibility until they do another one. | 2018-02-09 | 2018-02-12
Vine transit should have its invincibility start up after the first animation finishes | 2018-02-09 | 2018-02-12
Live Vine Transits don't pass through each other, if both players pick life and try to transit through at the same time. | 2018-02-09 | 2018-02-12
You can charge while crouching, and it messes up animations | 2018-02-09 | 2018-02-12
Player 1 can't go to main menu at the end of a round. Possibly related to the pause bug from before? | 2018-02-09 | 2018-02-27
Invincibility doesn't work with hitboxes with specific layers | 2018-02-09
Builds are fucked | 2018-01-25
Throws apply pushback when they shouldn't, relating to the zone of the attack ('t') not getting set properly. | 2018-01-24 | 2018-01-25
Hitsparks do not appear | 2017-01-19 | 2017-01-19
Getting hit can occasionally freeze you if you're moving | 2018-01-18
You can tap charge to charge while moving | 2017-12-11 | 2018-01-16
Characters can hit twice with the same attack | 2017-12-04
Menus on timing out don't work all the time | 2017-11-15 | 2018-02-06
Holding back while using L214E causes weird visual issues | 2017-11-15 | 2017-12-04
Pushback on the Vine Trap ends sooner than intended | 2017-11-15 | 2017-11-29
One button did not light up | 2017-11-14 | 2017-11-14
Nanocon Bugs | 2017-11-11 | 2018-02-12
Super Meter extends beyond what it looks like it should graphically | 2017-11-07 | 2017-11-08
Pushbox on top of characters doesn't disappear when using L214E | 2017-11-01 | 2017-11-03
Moving up while getting hit causes some graphical issues. | 2017-10-31 | 2017-12-04
Camera does not zoom | 2017-10-19 | 2017-12-01
Fireballs do not destroy on the edge of the stage | 2017-10-19 | 2017-11-06
Attacking right before hitting the ground causes the animation to continue. | 2017-10-17 | 2017-11-11
The pushboxes push players out when they're not supposed to. | 2017-10-12 | 2017-12-04
Player 2 Doesn't turn around when crossed up | 2017-10-11 | 2017-10-11